## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ganesh |  | Sentiment analysis misclassifies neutral sentiments as negative. | Sprint 1 | mentor | Functional | Adjusted training data and thresholds. | 2025-01-25 | Closed | Resolved with improved dataset.
2 | Ganesh |  | Keyword-based escalation misses complex phrases indicating urgency. | Sprint 2 | mentor | Functional | Proposed advanced NLP for synonyms. | 2025-01-26 | Open | Pending advanced NLP implementation.
3 | Ganesh |  | Response automation generates incomplete replies for unmatched issues. | Sprint 3 | mentor | Functional | Working on fallback response logic. | 2025-01-27 | Open | In Progress.
4 | Ganesh |  | Text embedding model clusters unrelated tickets incorrectly. | Sprint 1 | mentor | Algorithmic | Improved clustering algorithm. | 2025-01-25 | Closed | Issue resolved with revised logic.
5 | Ganesh |  | API integration fails under certain edge case conditions. | Sprint 2 | mentor | Integration | Enhanced API error handling. | 2025-01-26 | Open | Requires additional testing.